## Slide 1: Sales Meeting
Field Assessments
1.15.2025

## Slide 2: Agenda
Review of Business Plan and Roadmap
CP Retirement Update
Product Changes
  SalesPersona dimension name changes
  FLP project
  PSP project
Pricing feedback and discussion
Q&A (submitted and others)

## Slide 3: 2025 Business Plan
Completion of CP retirement
Rollout of SalesPersona update
PSP Update
Exploring older product repurposing
FLP Project
Recruit2Go
Strategic Sales Engagement Strategy
Using PSP/Sales Persona to rewin business
Reengage opportunities (Farmer’s, CNO, etc.)

## Slide 4: Producer Assessments Roadmap – 2024-2025
 |  | Q1 2024 | Q2 2024 | Q3 2024 | Q4 2024 | Q1 2025 | Q2 2025
1. Align on Purpose & Goals | RESEARCH |  |  |  |  |  | 
#2 Define the Execution Plan #3 Identify the Impact | DEVELOPMENT |  |  |  |  |  | 
4. Assign The Work | PLANNING |  |  |  |  |  | 
5. Track Progress | EXECUTION DELIVERY |  |  |  |  |  | 
6. Celebrate Success | LAUNCHED |  |  |  |  |  | 
Business Planning for 2025
BP Execution Plan and Impact
BP Assignment of Tasks
SuccessPredictor US Standard Scoring Update
Marketing Plan Execution
CP Transition Planning
Marketing Plan and Implementation
RC Pricing
Review
Priority Product Planning/Business Planning for 2024
SLCP Update
Competitor Analysis Update
Career Profile Transition Plan Development
SLCP Launch
SuccessPredictor Standard Scoring Update
CP Removed from Pilot and Sales Offering
Pilot Program Guidelines
SuccessPredictor MLEA Scoring Update
SuccessPredictor Canada Scoring Update
Farmers’ RFP Completion
SuccessPredictor MLEA Scoring Update
Strategic Selection Committee Interest
Working Sessions for Field Assessments (might be better positioned in “Work” section?)
SalesPersona Update
CP Retirement Alignment
CP Transition (ongoing)
FLP Discovery Project
PSP Updates
Thought Leadership development for Marketing
SalesPersona Update Launch

## Slide 5: Producer Assessments Roadmap – 2025-2026
 |  | Q3 2025 | Q4 2025 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026
1. Align on Purpose & Goals | RESEARCH |  |  |  |  |  | 
#2 Define the Execution Plan #3 Identify the Impact | DEVELOPMENT |  |  |  |  |  | 
4. Assign The Work | PLANNING |  |  |  |  |  | 
5. Track Progress | EXECUTION DELIVERY |  |  |  |  |  | 
Celebrate Success | LAUNCHED |  |  |  |  |  | 
Business Planning for 2026
BP Execution Plan and Impact
Business Planning for 2027
BP Execution Plan and Impact
BP Assignment of Tasks
CP Retired
BP Assignment of Tasks
RC Pricing
Review
RC Pricing
Review
CP Transition (ongoing)
PSP Relaunch Planning
PSP Potential Relaunch
FLP Changes (if necessary)

## Slide 6: Planning and Aligning Framework

## Slide 7: CP Retirement Update
Transition of contract companies
Alfa, Kansas City in progress
Working with Tier I within NOP Commerce Framework
Developing a communication plan for non-contract members
Full business plan to be established by end of January 2025
Monthly check-ins to ensure alignment and deadlines met

## Slide 8: SalesPersona Changes
Based on member feedback and input
Changes to dimension names only
Openness to Adaptability
Authenticity to Self-Awareness
No changes to scoring or reporting
Updates include documentation in the Resource Library
Goal to have updates in place February 1, 2025.

## Slide 9: FLP Update Project
Joint effort of Ben and Carolyn
Bi-weekly meeting cadence
Dimension mapping to recent Marketfacts survey in progress
Looking at viability of matching member needs to dimensions already in FLP
Developing quick survey to field to member companies
Goal to be completed mid to late Q1 – brief questionnaire to be fielded to member companies
Analysis of results and next steps to be determined after responses collected

## Slide 10: PSP Update Project
To be added to Engineering Priorities in Q1
No anticipated scoring changes – updates should be to reporting only
Upon completion, will work with Marketing to orchestrate relaunch
Special attention paid to Entrepreneurial Spirit dimension
Needs North American validation to determine if viable for a separate assessment
Should allow us to better compete with Culture Index and POP

## Slide 11: Pricing Feedback and Discussion
New pricing structure – how is it going?
Member feedback
Suggestions for process improvement
Other concerns?

## Slide 12: Q&A
Submitted questions:
Student and Non student issue – is there something we can change on the reports to make it less confusing for those that were used to CP having two versions (where it becomes biggest issue is when lack of financial experience prints out with students – can we just suppress that?, other ideas?)
Not sure if it’s worth revisiting how we might incorporate Entrepreneurial Traits in with Success Predictor? We had a discussion about this last year where Career Choice caught the eye of Farm Bureau because it has that specific dimension on the report but we can’t pivot to that because it’s not validated for U.S.
Other questions?

## Slide 13: Thank you!