## Slide 1: AI in Action: Enhancing Service and Strategy in Contact Centers
Consortium Research Proposal | Applied Research Solutions | September 2025

## Slide 2: Background and Context
AI is having increasing influence in contact centers, with growing interest in its potential to improve service delivery and operational efficiency.
Some organizations are experimenting with AI tools like virtual assistants and support technologies, but the extent and impact of adoption remain unclear.
This study will explore current state and future potential of AI in carrier contact centers, as well as consumer perceptions of interacting with AI-powered tools.
The study’s goal is to benchmark AI adoption, measure operational impact, and assess consumer experience to support more informed and effective uses of AI in this evolving service environment.
Notes: Why are we think it’s important to look at this topic, and why now – members are looking for opportunities to streamline processes, create operational efficiencies, and meet customer expectations.
Growing interest in the potential of AI to improve service delivery and operational efficiency
Some are already experimenting, but extent and impact remain unknown – where everyone thinks they are vs where they truly are – move beyond anecdotal to measuring real results
Consumer perspective is important

## Slide 3: Objectives
Benchmark AI Adoption: Map current AI use and maturity across carrier contact centers.
Assess Consumer Experience: Measure customer perceptions of AI in service, including trust, clarity, and satisfaction.
Measure Operational Impact: Evaluate effects on key metrics like Average Handle Time (AHT), Customer Satisfaction (CSAT), Net Promoter Score (NPS), and resolution rates.
Explore Compliance and Ethics: Examine how companies address transparency, fairness, and regulatory alignment.

## Slide 4: Key Research Questions
How do customers experience AI-driven service in the context of financial products?
What factors influence trust and satisfaction in AI-led interactions?
How does AI affect customer understanding of complex products?
How do AI-human handoffs affect customer trust, clarity, and overall experience?
Are there differences across demographic groups?
What types of AI tools are being used, and for what functions?
How is AI impacting key performance metrics?
What are the operational and compliance implications of AI integration?
How are organizations managing the balance between automation and human service?
How are customer journeys being designed to support smooth AI-human handoffs?
Track One: Consumer Experiences
Track Two: Carrier Practices

## Slide 5: Project Approach
Two quantitative research tracks will be designed to examine the role of AI in carrier contact centers.
Track One: Consumer Experience
  A sample of 1,600 responses will be collected through a 12-minute quantitative survey of current life insurance or annuity owners and non-owners across all age groups.
Track Two: Carrier Practices – Operational and Strategic Implementation
  The Sponsor Group will provide operational data to support analysis.
Sponsors will help shape the research instruments to ensure the study reflects their priorities and operational realities.

## Slide 6: Deliverables
Project kickoff deck and recording
Project plan
Input into the instruments (Tracks 1 and 2)
Final instruments (Tracks 1 and 2)
PowerPoint report of results
Virtual presentation of key findings and considerations

## Slide 7: Anticipated Timeline & Fees
Milestone | Timeline
Hold kickoff meeting | Week 1
Track 1: Consumer Experiences | 
Survey Instrument Development | Weeks 2-4
Survey Programming and Testing | Week 5
Data Collection | Weeks 6-7
Data Cleaning and Processing | Week 8
Track 2: Carrier Practices | 
Survey Instrument Development | Weeks 4-6
Survey Programming and Testing | Week 7
Data Collection | Weeks 8-10
Data Cleaning and Processing | Week 11
Analysis and Report Development | Weeks 11-13
Delivery of Results | Week 14
Discussion of Key Findings and Considerations | Week 15
Fees are subject to +/- 10% contingency. Although there is no travel expected for this project, fees do not include travel expenses which are additional and will be billed at cost.
The overall project timeline will be dependent on the sponsors’ responsiveness and timely submission of data.
Fees for this project are estimated to be $17,500 per sponsor
LIMRA anticipates completing this project within 15 weeks

## Slide 8: Sponsor Benefits
Sponsor Experience
Utilize LIMRA’s Expertise
Benchmark Against Peers
Influence Study Design
Share Research Costs
Gain Exclusive Access
Engage in Collaboration
Rely on a proven track record in research.
Compare results against a select peer group.
Shape the study’s topic areas and questions.
Reduce expenses through shared research funding.
Obtain data and insights not available to others.
Discuss and share insights with other sponsors.

## Slide 9: Our Organization and Brands

## Slide 10: Applied Research Solutions Team

## Slide 11: LIMRA Applied Research Solutions